## User Stories
Issue Type | Story ID | Epic | Module | Summary | Persona | User Story | Acceptance Criteria | Priority | Story Points | Demo Milestone | Dependencies | Component | Labels | Notes
Story | SMP-US-001 | E01 - Project Readiness and Design Freeze | M01 | Freeze requirement baseline v1.1 | Product Owner / Architect | As a Product Owner, I want the requirement, UI, DDL and ERD baselines frozen so that development starts from an agreed scope. | - Requirement document version is marked v1.1 - DDL_SCHEMA.sql is marked as source of truth - UI screen document is aligned with Company User ID, first login password change and Excel import rules - ERD table names match DDL table names - Open changes are logged as sprint backlog items, not informal changes | Highest | 2 | Demo 0 |  | Documentation | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-002 | E01 - Project Readiness and Design Freeze | M01 | Create Jira project structure | Scrum Master | As a Scrum Master, I want epics, stories, components, labels and demo milestones configured in Jira so that the team can track delivery consistently. | - Jira project has epics matching M01 to M20 delivery areas - Components include Backend, Frontend, Database, DevOps, QA, Documentation - Story template includes acceptance criteria, dependencies and demo milestone - Definition of Ready and Definition of Done are published - Backlog is ordered by dependency and MVP priority | Highest | 2 | Demo 0 | SMP-US-001 | Scrum | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-003 | E01 - Project Readiness and Design Freeze | M01 | Create API and coding standards | Architect | As an Architect, I want API, package, DTO, validation and error handling standards defined so that developers implement consistently. | - Standard package structure is documented - API versioning follows /api/v1 - DTOs are mandatory and JPA entities are not exposed - public_id is used in APIs instead of internal numeric IDs - Error response includes timestamp, message and correlation ID | Highest | 3 | Demo 0 | SMP-US-001 | Architecture | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-004 | E01 - Project Readiness and Design Freeze | M19 | Define test strategy and quality gates | QA Lead | As a QA Lead, I want unit, integration, API, UI and UAT quality gates agreed so that every story is testable from day one. | - JUnit 5 and Mockito are mandatory for backend services - MockMvc tests cover controller/security behavior - JaCoCo minimum coverage is configured - Critical E2E journeys are listed - UAT sign-off checklist is created | Highest | 3 | Demo 0 | SMP-US-001 | QA | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-005 | E02 - Project Foundation and Local Environment | M01 | Create Spring Boot backend skeleton | Developer | As a developer, I want a Spring Boot 3.x Java 21 backend skeleton so that backend development can start consistently. | - Maven project builds successfully - Package structure includes config, controller, service, repository, entity, dto, mapper, exception, security, audit and util - Spring Boot application starts with dev profile - Actuator health endpoint is available - No business APIs are implemented beyond health and base configuration | Highest | 5 | Demo 1 | SMP-US-003 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-006 | E02 - Project Foundation and Local Environment | M01 | Create Angular frontend shell | Frontend Developer | As a developer, I want an Angular 17+ application shell so that feature screens can be added consistently. | - Angular app builds successfully - Angular Material is installed - Header, sidebar and content layout are created - Environment files for dev, qa and prod exist - Initial routes are created for login and dashboard placeholders | Highest | 5 | Demo 1 | SMP-US-003 | Frontend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-007 | E02 - Project Foundation and Local Environment | M01 | Configure backend profiles and common properties | Developer | As a developer, I want dev, qa and prod profiles so that each environment can use correct configuration. | - application.yml contains common settings - application-dev.yml uses local MySQL - application-qa.yml and application-prod.yml use environment variables - Hibernate ddl-auto is validate - Sensitive values are not hardcoded in qa/prod | Highest | 3 | Demo 1 | SMP-US-005 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-008 | E02 - Project Foundation and Local Environment | M01 | Configure Swagger/OpenAPI | Developer | As a developer, I want Swagger/OpenAPI enabled so that APIs are easy to test and share. | - Swagger UI is accessible in dev - API metadata includes project name and version - Auth header support is configured - Controllers later added will appear automatically - Swagger is disabled or protected in prod as per environment policy | High | 2 | Demo 1 | SMP-US-005 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-009 | E02 - Project Foundation and Local Environment | M01 | Implement global exception and API response model | Developer | As a developer, I want standard API success and error responses so that frontend error handling is consistent. | - GlobalExceptionHandler is created - Validation errors return field-level messages - Not found returns 404 - Unauthorized returns 401/403 - Correlation ID is included in error response | High | 3 | Demo 1 | SMP-US-005 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-010 | E02 - Project Foundation and Local Environment | M01 | Configure logging and correlation ID | Developer | As a support engineer, I want every request traceable with a correlation ID so that defects can be investigated quickly. | - Correlation ID filter generates ID if missing - Correlation ID appears in logs - API response includes correlation ID for failures - No passwords or tokens are logged - Unit test covers correlation ID generation | Medium | 3 | Demo 1 | SMP-US-009 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-011 | E02 - Project Foundation and Local Environment | M18 | Create local build and run instructions | Developer | As a new team member, I want simple local setup instructions so that I can run backend, frontend and database without dependency confusion. | - README explains prerequisites - Commands are provided for MySQL setup - Commands are provided for backend start - Commands are provided for frontend start - Troubleshooting section covers common errors | High | 2 | Demo 1 | SMP-US-005,SMP-US-006 | Documentation | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-012 | E03 - Database, Flyway and Reference Data | M01 | Create local MySQL database scripts | Developer | As a developer, I want local database setup scripts so that the database can be created consistently. | - 00_create_database.sql creates skill_matrix_db - 01_create_local_user.sql creates local user with agreed username/password - 02_drop_database.sql is available for dev reset - README_DB_SETUP.md matches the script credentials - Scripts are not used for production credentials | Highest | 3 | Demo 1 | SMP-US-001 | Database | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-013 | E03 - Database, Flyway and Reference Data | M01 | Finalize V01 initial schema migration | Developer | As a developer, I want the full DDL converted into Flyway V01 so that schema creation is automated. | - V01__initial_schema.sql contains tables, PKs, FKs, indexes and constraints - No seed data is mixed into V01 except strictly required technical defaults - refresh_tokens table exists - users supports must_change_password and account lock fields - Flyway migration succeeds on a fresh database | Highest | 8 | Demo 1 | SMP-US-012 | Database | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-014 | E03 - Database, Flyway and Reference Data | M02 | Create V02 master reference seed data | Developer | As an Admin, I want baseline lookup, role, rating and application hierarchy reference data seeded so that screens can show valid dropdowns. | - Roles ADMIN, LEAD_MANAGER and TECHNICIAN are seeded - Lookup types and lookup values are seeded - Rating scale 1 to 5 is seeded - Account, Application Types WEB/HOST, Bundles B06/B12/B20 and portfolios are seeded - Seed script is idempotent for clean Flyway execution | Highest | 5 | Demo 1 | SMP-US-013 | Database | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-015 | E03 - Database, Flyway and Reference Data | M01 | Create V03 dev demo data | Developer | As a demo user, I want realistic demo data so that sprint demos can be shown before full production data is available. | - Demo data exists only in dev-migration - Demo users include Admin, Lead Manager and Technicians - Demo ATLAS-deZentral application data is available - Demo data supports login, assignment, assessment and review workflow - Production profile does not execute dev demo data | High | 5 | Demo 1 | SMP-US-014 | Database | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-016 | E03 - Database, Flyway and Reference Data | M01 | Create verification query suite | Developer | As a developer, I want verification queries so that DB setup can be validated after migration. | - verification_queries.sql checks table count - It verifies lookup data - It verifies roles and rating scale - It verifies sample users and application data - README explains expected results | Medium | 2 | Demo 1 | SMP-US-014 | Database | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-017 | E03 - Database, Flyway and Reference Data | M01 | Add Flyway Testcontainers validation test | Developer | As a developer, I want an integration test that runs Flyway on MySQL so that migration failures are caught early. | - Testcontainers MySQL starts during integration test - Flyway migrations execute successfully - Expected table count is asserted - Seed data count is asserted - Test runs in CI pipeline profile | High | 5 | Demo 1 | SMP-US-013 | QA | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-018 | E04 - Authentication, RBAC and First Login Security | M17 | Implement company user ID login API | User | As a user, I want to log in using my company user ID so that my identity aligns with corporate standards. | - Login request accepts companyUserId and password - companyUserId maps to users.username - Invalid credentials return generic error - Inactive users cannot login - Successful login returns user public_id, full name and roles | Highest | 5 | Demo 2 | SMP-US-013 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-019 | E04 - Authentication, RBAC and First Login Security | M17 | Implement password hashing and first login password change | Security Admin | As a Security Admin, I want temporary passwords to force immediate password change so that bulk-created accounts are secure. | - Passwords are stored only as BCrypt hashes - must_change_password is true for bulk-created users - User is redirected to change password after first login - All other pages/APIs are blocked until password is changed - After change, must_change_password becomes false and audit log is created | Highest | 8 | Demo 2 | SMP-US-018 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-020 | E04 - Authentication, RBAC and First Login Security | M17 | Implement JWT access token and refresh token flow | User | As a user, I want a secure session so that I can use the application without repeatedly logging in. | - Access token is short-lived - Refresh token is stored hashed in database - Refresh API issues new access token - Logout revokes refresh token - Expired/tampered tokens return 401 | Highest | 8 | Demo 2 | SMP-US-018,SMP-US-013 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-021 | E04 - Authentication, RBAC and First Login Security | M17 | Implement account lockout after failed attempts | Security Admin | As a Security Admin, I want accounts locked after repeated failures so that brute-force attempts are reduced. | - Failed login count increments on invalid password - Account locks after configured threshold - Locked account cannot login until lock expires or admin unlocks - Successful login resets failed count - Audit logs success and failure events | High | 5 | Demo 2 | SMP-US-018 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-022 | E04 - Authentication, RBAC and First Login Security | M17 | Implement frontend login and change password screens | User | As a user, I want clear login and password change screens so that I can access the platform securely. | - Login page label says Company User ID - Password field is masked - First login redirects to change password screen - Change password validates current password and new password rules - After password change user is redirected by role | Highest | 5 | Demo 2 | SMP-US-018,SMP-US-019 | Frontend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-023 | E04 - Authentication, RBAC and First Login Security | M17 | Implement role guards and sidebar visibility | User | As a user, I want to see only the menus allowed for my role so that the application is simple and secure. | - Admin sees admin menus - Lead Manager sees review, gap, dashboard and reports menus - Technician sees My Assessments and Notifications only - Direct URL access without permission returns 403 - Unit tests cover guard behavior | Highest | 5 | Demo 2 | SMP-US-020,SMP-US-006 | Frontend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-024 | E04 - Authentication, RBAC and First Login Security | M17 | Add AuthService and security tests | Developer | As a developer, I want JUnit and Mockito tests for authentication so that login security stays reliable. | - AuthServiceTest covers valid login - Invalid password is tested - Inactive user is tested - Account lockout is tested - Refresh and logout are tested - MockMvc tests verify 401 and 403 | High | 5 | Demo 2 | SMP-US-018,SMP-US-020 | QA | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-025 | E05 - Lookup and Application Hierarchy | M02 | Implement lookup management APIs | Admin | As an Admin, I want to manage lookup values so that statuses and dropdowns can evolve without DDL changes. | - List lookup types API works - List active lookup values by type works - Create/update lookup value works - System values cannot be deleted - Audit log is created for changes | High | 5 | Demo 3 | SMP-US-014,SMP-US-020 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-026 | E05 - Lookup and Application Hierarchy | M02 | Implement lookup management UI | Admin | As an Admin, I want lookup management screens so that I can maintain configurable values. | - Lookup types list is displayed - Lookup values are displayed by selected type - Create/edit dialog validates required fields - Inactive values are hidden from active dropdowns - Error messages are shown clearly | Medium | 5 | Demo 3 | SMP-US-025 | Frontend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-027 | E05 - Lookup and Application Hierarchy | M03 | Implement application type, bundle and portfolio APIs | Admin | As an Admin, I want APIs for application type, bundle and portfolio so that Web/Host and B06/B12/B20 hierarchy is controlled centrally. | - GET application types returns WEB and HOST - GET bundles supports applicationTypeCode filter - Portfolio list supports account, application type and bundle - Only active values appear by default - Deprecated/future values can be included when requested | Highest | 5 | Demo 3 | SMP-US-014 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-028 | E05 - Lookup and Application Hierarchy | M03 | Implement application CRUD APIs | Admin | As an Admin, I want to create and maintain applications under portfolio so that changing applications does not require DDL changes. | - Create application under selected portfolio - Duplicate application code in same portfolio is blocked - Update application details works - Deprecate application without physical delete - Historical reports can include deprecated apps | Highest | 8 | Demo 3 | SMP-US-027 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-029 | E05 - Lookup and Application Hierarchy | M03 | Implement cascading application dropdown APIs | User | As a user, I want Application Type, Bundle and Application dropdowns so that I can select the correct application context. | - WEB + B06 returns only B06 Web apps - HOST + B06 returns only B06 Host apps - WEB + B12 returns only B12 Web apps - HOST + B12 returns only B12 Host apps - B20 is future-ready - Deprecated apps are hidden by default | Highest | 5 | Demo 3 | SMP-US-027,SMP-US-028 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-030 | E05 - Lookup and Application Hierarchy | M03 | Implement application hierarchy UI | Admin | As an Admin, I want application hierarchy screens so that I can manage Web/Host, bundles, portfolios and applications. | - Application Type and Bundle lists are visible - Portfolio screen filters by account/type/bundle - Application screen has cascading filters - Create/edit application dialog validates duplicate codes - Lifecycle status is shown with chips | High | 8 | Demo 3 | SMP-US-027,SMP-US-028,SMP-US-029 | Frontend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-031 | E05 - Lookup and Application Hierarchy | M03 | Add application hierarchy tests | Developer | As a developer, I want tests for application hierarchy so that dropdown and lifecycle behavior remains stable. | - Service tests cover WEB/HOST and B06/B12/B20 filters - Duplicate application code test exists - Deprecated app hidden/visible logic is tested - Repository queries are integration-tested where needed - MockMvc tests cover API authorization | High | 5 | Demo 3 | SMP-US-027,SMP-US-029 | QA | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-032 | E06 - User, Team and Technician Assignment | M04 | Implement user management APIs | Admin | As an Admin, I want to create and maintain users so that all technicians, leads and admins are available in the system. | - Create user with Company User ID, full name, email, employee ID and active flag - Duplicate company user ID is blocked - Duplicate email is blocked - Update user works - Deactivate user prevents login | Highest | 8 | Demo 4 | SMP-US-020 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-033 | E06 - User, Team and Technician Assignment | M04 | Implement role assignment APIs | Admin | As an Admin, I want to assign system roles so that users get correct access. | - Assign ADMIN, LEAD_MANAGER or TECHNICIAN role - One primary role can be set - Multiple roles are supported - Role changes are audited - User roles are returned in auth/me response | Highest | 5 | Demo 4 | SMP-US-032 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-034 | E06 - User, Team and Technician Assignment | M04 | Implement team management APIs | Admin | As an Admin, I want to create teams and map users so that lead/team ownership can be tracked. | - Create/update team works - Map users to team works - Mark team lead works - Team filter is available in user list - Audit log is created | Medium | 5 | Demo 4 | SMP-US-032 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-035 | E06 - User, Team and Technician Assignment | M04 | Implement user management UI | Admin | As an Admin, I want a user management screen so that I can manage 140 technicians and leads. | - User list supports search/filter by Company User ID, name, email, role and status - Create/edit user form is available - Assign roles and teams from UI - Deactivate/reactivate user from UI - Validation messages are clear | Highest | 8 | Demo 4 | SMP-US-032,SMP-US-033 | Frontend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-036 | E06 - User, Team and Technician Assignment | M14 | Implement User Master Excel import | Admin | As an Admin, I want to bulk upload 140 technicians so that initial onboarding is faster and controlled. | - Downloadable User Master template exists - Upload validates Company User ID, email, role and active flag - System creates users with generated/temporary password hash - must_change_password is set for imported users - Import history captures total, success and error rows | Highest | 8 | Demo 4 | SMP-US-032,SMP-US-019 | Backend/Frontend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-037 | E06 - User, Team and Technician Assignment | M05 | Implement technician application assignment APIs | Admin / Lead Manager | As an Admin or Lead Manager, I want to assign technicians to one or more applications so that their assessment scope is controlled. | - Assign user to application with role_on_app, allocation and effective dates - Same user can support multiple applications - Duplicate active assignment is blocked - Expired assignments are excluded from active views - Assignment history is retained | Highest | 8 | Demo 4 | SMP-US-029,SMP-US-032 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-038 | E06 - User, Team and Technician Assignment | M05 | Implement technician assignment UI | Admin / Lead Manager | As an Admin or Lead Manager, I want a technician assignment screen so that I can maintain application responsibility. | - Cascading filter Application Type -> Bundle -> Application works - Technician autocomplete works - Role on Application dropdown includes PRIMARY, BACKUP, SME, TRAINEE and other configured values - Allocation and effective dates are validated - Deactivation works without physical delete | High | 8 | Demo 4 | SMP-US-037 | Frontend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-039 | E06 - User, Team and Technician Assignment | M14 | Implement Technician Assignment Excel import | Admin | As an Admin, I want to bulk upload technician application assignments so that multi-application mappings can be created quickly. | - Template uses Company User ID and Application Code, not numeric IDs - Validation confirms application belongs to selected type and bundle - Role_on_app is validated against lookup - Allocation above 100 per user shows warning or configurable error - All-or-nothing import behavior is applied | High | 8 | Demo 4 | SMP-US-036,SMP-US-037 | Backend/Frontend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-040 | E06 - User, Team and Technician Assignment | M04/M05 | Add user and assignment tests | Developer | As a developer, I want JUnit/Mockito tests for users and assignments so that onboarding logic is stable. | - UserServiceTest covers create/update/deactivate - Duplicate username/email tests exist - UserApplicationMappingServiceTest covers multi-application assignment - Invalid allocation and date validation tests exist - Import service tests cover valid and invalid files | High | 5 | Demo 4 | SMP-US-032,SMP-US-037,SMP-US-036 | QA | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-041 | E07 - Skill Master and Rating Scale | M06 | Implement skill category APIs | Admin | As an Admin, I want to manage skill categories so that skills can be grouped properly. | - Create/update skill category works - Duplicate category code is blocked - Deactivate category is supported if unused or per business rule - Skill categories are returned for dropdowns - Audit log is created | High | 5 | Demo 5 | SMP-US-025 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-042 | E07 - Skill Master and Rating Scale | M06 | Implement skill master APIs with three-category model | Admin | As an Admin, I want to manage common technical skills, application know-how and VW tools without changing DDL. | - Skill supports category group TECHNICAL_SKILL, APP_KNOWLEDGE and VW_TOOL - Skill type supports TECHNICAL, PROCESS, APP_KNOWLEDGE and TOOL - Scope supports GLOBAL, WEB, HOST, VW_GLOBAL and APP-specific values - Duplicate skill code is blocked - Inactive skills are hidden from new requirement setup | Highest | 8 | Demo 5 | SMP-US-041 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-043 | E07 - Skill Master and Rating Scale | M06 | Implement rating scale APIs | Admin / User | As a user, I want to see the 1 to 5 rating scale so that skill ratings are understood consistently. | - Rating scale API returns levels 1 to 5 - Each level includes name and description - Rating scale is read-only for most users - Admin can view rating details - Frontend can reuse rating scale in dropdowns | Medium | 3 | Demo 5 | SMP-US-014 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-044 | E07 - Skill Master and Rating Scale | M06 | Implement skill management UI | Admin | As an Admin, I want skill category and skill screens so that I can maintain the skill catalogue. | - Skill category list and edit screens exist - Skill list filters by category, type, scope and active status - Skill form supports skill category group, type and scope - Technical skills are clearly marked as reusable/global - Duplicate errors are shown clearly | High | 8 | Demo 5 | SMP-US-042 | Frontend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-045 | E07 - Skill Master and Rating Scale | M14 | Implement Common Technical Skill Excel import | Admin | As an Admin, I want to upload common technical skills once so that all applications can reuse them. | - Template 01_COMMON_TECH_SKILLS is available - Technical skills are inserted once into skills table - No per-application duplicate technical skills are created - Validation rejects duplicate skill codes - Import preview shows valid and error rows | Highest | 8 | Demo 5 | SMP-US-042 | Backend/Frontend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-046 | E07 - Skill Master and Rating Scale | M14 | Implement Application Specific Skill Excel import | Application Lead | As an Application Lead, I want to upload application-specific know-how and VW tools for my application so that requirements can be tailored. | - Template 02_APP_SPECIFIC_SKILLS_<APP> is supported - Application-specific skills use APP:<Application_Code> scope - VW tools can be VW_GLOBAL, WEB, HOST or APP-specific - Validation checks application code if APP scope is used - Import history is captured | High | 8 | Demo 5 | SMP-US-042,SMP-US-029 | Backend/Frontend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-047 | E07 - Skill Master and Rating Scale | M06/M14 | Add skill master and skill import tests | Developer | As a developer, I want tests for skill APIs and imports so that skill catalogue quality is controlled. | - SkillServiceTest covers create/update/deactivate - Duplicate skill code test exists - Common technical skill import prevents duplicates - Application-specific skill import validates scope - Invalid Excel file returns row-level errors | High | 5 | Demo 5 | SMP-US-042,SMP-US-045,SMP-US-046 | QA | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-048 | E09 - Requirement Version and Expected Ratings | M07 | Implement requirement version APIs | Admin | As an Admin, I want to create requirement versions per application so that expected skills are version-controlled. | - Create draft requirement version for application - Version code is unique per application - Effective dates are validated - Draft version can be updated - Approved version cannot be directly edited | Highest | 8 | Demo 6 | SMP-US-029,SMP-US-042 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-049 | E09 - Requirement Version and Expected Ratings | M07 | Implement expected ratings APIs | Admin | As an Admin, I want to add expected skills and levels to a requirement version so that assessment criteria are defined. | - Add skill to requirement version - Same skill cannot be duplicated in same version - Expected level must be 1 to 5 - Criticality, min_people and mandatory flag are required - Expected ratings can be updated while version is Draft | Highest | 8 | Demo 6 | SMP-US-048 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-050 | E09 - Requirement Version and Expected Ratings | M07 | Implement publish and approve requirement workflow | Admin / Lead Manager | As an Admin and Lead Manager, I want requirement versions to be approved before assessment so that requirements are governed. | - Admin can publish draft version - Lead Manager can approve or reject - Rejection requires reason - Only approved versions can be selected in assessment cycle - Audit log captures publish/approve/reject | Highest | 8 | Demo 6 | SMP-US-048,SMP-US-049 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-051 | E09 - Requirement Version and Expected Ratings | M07 | Implement requirement version UI | Admin / Lead Manager | As an Admin or Lead Manager, I want a requirement version screen so that I can manage expected skills per application. | - Filter by Application Type, Bundle and Application - List shows version code, status, skills count and actions - Draft version skill grid supports add/update/remove - Lead Manager approval panel supports approve/reject - Expected levels are visible to Admin/Lead Manager only | Highest | 8 | Demo 6 | SMP-US-048,SMP-US-050 | Frontend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-052 | E09 - Requirement Version and Expected Ratings | M14 | Implement Requirement Mapping Excel import | Admin / Application Lead | As an Admin, I want to upload application requirement mapping so that expected ratings can be created quickly. | - Template 03_APP_REQUIREMENT_MAPPING_<APP> is supported - Application Type, Bundle and Application Code are validated - Common technical skills can be mapped without duplicating skills - Application-specific skills can be mapped only to valid applications - Requirement version and expected_ratings are created/updated in Draft only | Highest | 8 | Demo 6 | SMP-US-045,SMP-US-046,SMP-US-048 | Backend/Frontend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-053 | E09 - Requirement Version and Expected Ratings | M07/M14 | Add requirement version tests | Developer | As a developer, I want tests for requirement version, expected rating and import behavior so that governance rules are safe. | - RequirementVersionServiceTest covers create, publish, approve and reject - Duplicate skill in version test exists - Approved version edit is blocked - Requirement import validates references - Lead Manager security scope is tested | High | 5 | Demo 6 | SMP-US-048,SMP-US-050,SMP-US-052 | QA | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-054 | E10 - Assessment Cycle | M08 | Implement assessment cycle APIs | Admin | As an Admin, I want to create and manage assessment cycles so that technicians can submit within controlled periods. | - Create cycle for approved requirement version - Start and end dates are validated - Only one open cycle per application is allowed or warned per configuration - Open/close status changes work - Closed cycles are read-only | Highest | 8 | Demo 7 | SMP-US-050 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-055 | E10 - Assessment Cycle | M08 | Implement assessment cycle UI | Admin | As an Admin, I want an assessment cycle screen so that I can open and close assessment windows. | - Filter by Application Type, Bundle and Application - Cycle list shows status, dates and requirement version - Create cycle form shows approved versions only - Open/close actions are available - Historical cycles are viewable | High | 5 | Demo 7 | SMP-US-054 | Frontend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-056 | E10 - Assessment Cycle | M08 | Add cycle tests | Developer | As a developer, I want tests for assessment cycles so that cycle rules are reliable. | - Cannot create cycle with draft/rejected requirement version - End date before start date is rejected - Closed cycle blocks submission - Open cycle retrieval works - MockMvc security tests exist | High | 3 | Demo 7 | SMP-US-054 | QA | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-057 | E11 - Technician Self Assessment | M09 | Implement assigned application API for technician | Technician | As a Technician, I want to see only my active assigned applications so that I submit assessment only for my responsibilities. | - API returns only active assignments - Expired assignments are excluded - Application dropdown uses WEB/HOST and bundle context - Technician cannot see unassigned applications - Admin/Lead Manager behavior is separately controlled | Highest | 5 | Demo 7 | SMP-US-037,SMP-US-054 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-058 | E11 - Technician Self Assessment | M09 | Implement self-assessment load API | Technician | As a Technician, I want the system to load skills for my assigned application and open cycle so that I can rate myself. | - API loads skills from approved requirement version - Expected level is not returned in technician response - Mandatory flag and skill category are returned - Draft/submitted status is returned - No open cycle returns clear message | Highest | 8 | Demo 7 | SMP-US-054,SMP-US-057 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-059 | E11 - Technician Self Assessment | M09 | Implement save draft self-assessment API | Technician | As a Technician, I want to save draft ratings so that I can complete assessment in multiple sessions. | - Draft save allows partial ratings - Technician can update own draft - Technician cannot update another user's draft - Draft does not notify Lead Manager - Audit log is captured as SAVE_DRAFT | High | 5 | Demo 7 | SMP-US-058 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-060 | E11 - Technician Self Assessment | M09 | Implement final submit self-assessment API | Technician | As a Technician, I want to submit final assessment so that my Lead Manager can review it. | - Mandatory skills require ratings - Evidence is required for self-rating 4 or 5 - Submitted assessment becomes read-only - Review task/notification is generated - Submission after cycle close is blocked | Highest | 8 | Demo 7 | SMP-US-059 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-061 | E11 - Technician Self Assessment | M09 | Implement technician self-assessment UI | Technician | As a Technician, I want a simple self-assessment screen so that I can rate skills and provide evidence. | - Application dropdown shows only assigned applications - Skill grid shows category, skill, mandatory, self rating, evidence and comments - Expected level column is never displayed - Save Draft and Submit Final buttons work - Status chip shows DRAFT, SUBMITTED, RETURNED or APPROVED | Highest | 8 | Demo 7 | SMP-US-058,SMP-US-060 | Frontend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-062 | E11 - Technician Self Assessment | M09/M17 | Add self-assessment tests including expected-level hiding | Developer | As a developer, I want self-assessment tests so that technician privacy and workflow rules are enforced. | - Technician assigned app filter is tested - Expected level not present in API response test exists - Draft save test exists - Submit validation tests exist - Closed cycle submission is blocked | Highest | 5 | Demo 7 | SMP-US-058,SMP-US-060 | QA | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-063 | E12 - Lead Manager Review and Approval | M10 | Implement pending review list API | Lead Manager | As a Lead Manager, I want to see technicians pending review for my applications so that I can prioritize approvals. | - Pending list filters by application - Only submitted assessments are shown - Lead Manager sees assigned scope only - Admin can see all scope - Pagination and search work | Highest | 5 | Demo 8 | SMP-US-060 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-064 | E12 - Lead Manager Review and Approval | M10 | Implement manager review grid API | Lead Manager | As a Lead Manager, I want to load a submitted assessment with expected and self ratings so that I can review accurately. | - Review grid shows expected level to Lead Manager - Self rating, evidence and technician comments are visible - Manager rating and comment are editable - Row decision defaults to pending - Technician cannot access review API | Highest | 8 | Demo 8 | SMP-US-063 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-065 | E12 - Lead Manager Review and Approval | M10 | Implement row-level review decisions | Lead Manager | As a Lead Manager, I want to approve, mark gap or request clarification per skill so that review is precise. | - Row decision can be APPROVED, GAP_IDENTIFIED or CLARIFICATION_NEEDED - Manager comment can be saved - Final rating is stored - Updates are audited - Invalid rating outside 1 to 5 is rejected | Highest | 5 | Demo 8 | SMP-US-064 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-066 | E12 - Lead Manager Review and Approval | M10 | Implement bulk review actions | Lead Manager | As a Lead Manager, I want bulk approve/gap/clarification actions so that large assessments can be reviewed efficiently. | - Bulk approve selected rows works - Bulk gap selected rows works - Bulk clarification selected rows works - Partial selection is supported - Each row action is auditable | High | 5 | Demo 8 | SMP-US-065 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-067 | E12 - Lead Manager Review and Approval | M10 | Implement overall approval and return workflow | Lead Manager | As a Lead Manager, I want to approve or return the full assessment so that the workflow moves forward correctly. | - Approve Ratings locks assessment - Approve triggers gap analysis - Return sends assessment back to technician - Overall note is stored - Notification is created for technician | Highest | 8 | Demo 8 | SMP-US-065 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-068 | E12 - Lead Manager Review and Approval | M10 | Implement Lead Manager review UI | Lead Manager | As a Lead Manager, I want a review screen with technician context and bulk actions so that I can efficiently validate assessments. | - Filter by Application Type, Bundle, Application and Technician works - Expected level is visible to Lead Manager - Bulk toolbar appears when rows selected - Overall decision panel is separate from row decisions - Approve and Return actions work | Highest | 8 | Demo 8 | SMP-US-064,SMP-US-067 | Frontend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-069 | E12 - Lead Manager Review and Approval | M10 | Add review workflow tests | Developer | As a developer, I want tests for Lead Manager review so that approvals are safe. | - Pending review scope test exists - Row decision update test exists - Bulk action tests exist - Approval triggers gap analysis test exists - Return makes technician assessment editable test exists | High | 5 | Demo 8 | SMP-US-064,SMP-US-067 | QA | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-070 | E13 - Gap Analysis and Training Recommendation | M11 | Implement gap calculation service | System | As a system, I want to calculate gaps after approval so that skill risk is objectively captured. | - Gap = expected level - final manager rating - No gap is recorded as resolved/none when final >= expected - Gap severity considers criticality - Historical snapshots are not overwritten - Calculation runs only after overall approval | Highest | 8 | Demo 8 | SMP-US-067 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-071 | E13 - Gap Analysis and Training Recommendation | M11 | Implement gap APIs | Lead Manager | As a Lead Manager, I want to view gaps by application, cycle and technician so that I can take action. | - Get gaps by cycle and technician works - Get gaps by application works - Get bundle-level gap summary works - Filters use application type and bundle codes - Only authorized scope is returned | High | 5 | Demo 8 | SMP-US-070 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-072 | E13 - Gap Analysis and Training Recommendation | M12 | Implement training recommendation generation | System | As a system, I want to generate training recommendations from gaps so that skill improvement actions are visible. | - Training is created only for valid gaps - Priority maps from severity - Target date maps to priority target days - Technician is added as participant - Duplicate recommendation for same gap is avoided | High | 8 | Demo 9 | SMP-US-070 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-073 | E13 - Gap Analysis and Training Recommendation | M12 | Implement gap and training UI | Lead Manager | As a Lead Manager, I want gap and training screens so that I can monitor improvement actions. | - Gap screen shows summary cards and detail table - Training screen filters by application, cycle, severity, priority and status - Training target date is visible - Confirm plan action works - Export action is available when report export is ready | High | 8 | Demo 9 | SMP-US-071,SMP-US-072 | Frontend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-074 | E13 - Gap Analysis and Training Recommendation | M11/M12 | Add gap and training tests | Developer | As a developer, I want tests for gap and training logic so that management reports are accurate. | - Gap severity mapping tests exist - Training priority and target date tests exist - No training for no-gap rows test exists - Duplicate generation test exists - Dashboard can consume gap snapshots | High | 5 | Demo 9 | SMP-US-070,SMP-US-072 | QA | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-075 | E14 - Dashboard and Reports | M13 | Implement dashboard summary APIs | Admin / Lead Manager | As management, I want summary metrics so that readiness and risk are visible at a glance. | - Summary API returns total applications, assessed applications, readiness, open gaps and pending training - Filters by Application Type and Bundle work - Application-level filter works - Metrics are based on approved assessment data - Unauthorized users cannot view out-of-scope data | High | 8 | Demo 9 | SMP-US-070,SMP-US-072 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-076 | E14 - Dashboard and Reports | M13 | Implement readiness and coverage risk APIs | Admin / Lead Manager | As management, I want readiness and coverage risk metrics so that backup gaps are identified early. | - Readiness percentage is calculated correctly - Coverage risk uses min_people from expected ratings - SME/backup coverage metrics are available - Historical cycle filters work - Performance target is acceptable for initial data volume | High | 8 | Demo 9 | SMP-US-075 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-077 | E14 - Dashboard and Reports | M13 | Implement dashboard UI | Admin / Lead Manager | As management, I want a dashboard with cards, readiness table and heatmap so that I can present status to stakeholders. | - Executive summary cards are displayed - Filter bar supports Application Type, Bundle, Application and Cycle - Application readiness table is shown - Skill heatmap is shown - Coverage risk panel highlights skills below threshold | High | 8 | Demo 9 | SMP-US-075,SMP-US-076 | Frontend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-078 | E14 - Dashboard and Reports | M13 | Implement reports APIs | Admin / Lead Manager | As management, I want gap, training and assessment reports so that data can be reviewed outside the tool. | - Gap report endpoint supports filters - Training demand report endpoint supports filters - Assessment status report endpoint supports filters - Pagination works - Report data matches dashboard totals | High | 5 | Demo 10 | SMP-US-075 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-079 | E14 - Dashboard and Reports | M13 | Implement reports UI | Admin / Lead Manager | As management, I want report screens with filters so that I can analyze gaps and training demand. | - Gap report screen works - Training demand report screen works - Assessment status report screen works - Filters persist during export - Empty results show friendly message | Medium | 5 | Demo 10 | SMP-US-078 | Frontend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-080 | E14 - Dashboard and Reports | M13/M14 | Implement Excel export APIs | Admin / Lead Manager | As a user, I want to export reports to Excel so that I can share them in management reviews. | - Gap report exports to .xlsx - Training plan exports to .xlsx - Assessment status exports to .xlsx - Excel headers and date formats are correct - Export action is logged in import_export_history | Medium | 5 | Demo 10 | SMP-US-078 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-081 | E14 - Dashboard and Reports | M13 | Add dashboard and report tests | Developer | As a developer, I want tests for dashboard and reports so that management metrics are trustworthy. | - Readiness calculation tests exist - Coverage risk tests exist - Heatmap data tests exist - Export file validity test exists - Report filters are tested | High | 5 | Demo 10 | SMP-US-075,SMP-US-080 | QA | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-082 | E08 - Excel Import and Export | M14 | Implement import history API and UI | Admin | As an Admin, I want to see all import/export history so that data loads are traceable. | - History list shows file name, entity type, operation, status, total/success/error rows and performed by - Error details are viewable - History is paginated - Filter by operation/entity/status works - Only Admin can access full history | Medium | 5 | Demo 10 | SMP-US-036,SMP-US-045,SMP-US-052 | Backend/Frontend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-083 | E08 - Excel Import and Export | M14 | Implement template download APIs | Admin / Application Lead | As an Admin or Application Lead, I want to download fixed Excel templates so that uploaded data follows required structure. | - User master template can be downloaded - User assignment template can be downloaded - Common technical skill template can be downloaded - App-specific skill template can be downloaded - Requirement mapping template can be downloaded | Medium | 5 | Demo 10 | SMP-US-036,SMP-US-045,SMP-US-052 | Backend/Frontend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-084 | E15 - Audit Log and Notifications | M15 | Implement audit logging service | Admin | As an Admin, I want all business actions audited so that changes can be traced. | - Audit service captures user, action, entity type, entity ID, old value, new value and timestamp - Passwords and tokens are never logged - Audit is written for create/update/submit/approve/reject/import/export - Audit failure does not expose sensitive data - Audit table has no update/delete APIs | High | 8 | Demo 10 | SMP-US-009 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-085 | E15 - Audit Log and Notifications | M15 | Implement audit log UI | Admin | As an Admin, I want an audit log screen so that I can investigate actions. | - Audit table shows timestamp, user, action, entity type and summary - Filters by date, user, action and entity type work - Expand row shows old/new JSON - Export audit works - Access restricted to Admin or approved read-only roles | Medium | 5 | Demo 10 | SMP-US-084 | Frontend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-086 | E15 - Audit Log and Notifications | M16 | Implement notification creation service | System | As a system, I want to create notifications for key events so that users know what action is needed. | - Assessment submitted creates Lead Manager notification - Assessment returned creates Technician notification - Assessment approved creates Technician notification - Training plan generated creates Technician/Lead notification - Notification failure does not roll back main transaction | Medium | 8 | Demo 10 | SMP-US-067,SMP-US-072 | Backend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-087 | E15 - Audit Log and Notifications | M16 | Implement notification UI | User | As a user, I want notification badges and a drawer so that I can see pending actions quickly. | - Header badge count shows unread notifications - Notification drawer shows recent notifications - Mark as read works - Notification click navigates to related screen - All roles can access their own notifications | Medium | 5 | Demo 10 | SMP-US-086 | Frontend | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-088 | E15 - Audit Log and Notifications | M15/M16 | Add audit and notification tests | Developer | As a developer, I want tests for audit and notifications so that traceability works reliably. | - Audit creation is tested - Sensitive data exclusion is tested - Notification generation by event is tested - Notification failure without rollback is tested - Security test verifies user sees own notifications only | Medium | 5 | Demo 10 | SMP-US-084,SMP-US-086 | QA | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-089 | E16 - Testing, Quality and UAT | M19 | Create backend unit test suite quality gate | QA / Developer | As a QA lead, I want backend unit test coverage enforced so that code quality is measurable. | - JaCoCo is configured - Overall backend coverage target is minimum 80% - Service layer target is minimum 85% - Build fails if quality gate fails - Coverage report is published in CI | High | 5 | Demo 11 | SMP-US-024,SMP-US-031,SMP-US-040 | QA | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-090 | E16 - Testing, Quality and UAT | M19 | Create API test collection | QA | As a QA engineer, I want a Postman/API collection so that all APIs can be regression-tested. | - Collection includes auth, master data, assignment, skills, requirements, assessment, review, gaps, reports and imports - DEV and QA environment variables exist - Positive and negative cases are covered - Collection can run in CI - API test report is generated | High | 5 | Demo 11 | SMP-US-080 | QA | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-091 | E16 - Testing, Quality and UAT | M19 | Create Angular unit and E2E test baseline | QA / Frontend Developer | As a QA engineer, I want frontend tests so that critical UI journeys are stable. | - Auth guard tests exist - Login screen tests exist - Self-assessment UI tests exist - Manager review UI tests exist - E2E flow Login -> Submit -> Review -> Approve is automated | High | 8 | Demo 11 | SMP-US-061,SMP-US-068 | QA | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-092 | E16 - Testing, Quality and UAT | M19 | Execute security testing | Security / QA | As a security reviewer, I want security validation so that the production release is safe. | - OWASP ZAP baseline scan executed - JWT tampering test passes - Role elevation test passes - SQL injection checks are performed - No sensitive data in logs is verified | Highest | 8 | Demo 11 | SMP-US-020,SMP-US-023 | QA | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-093 | E16 - Testing, Quality and UAT | M19 | Execute performance testing | QA | As a QA lead, I want performance testing so that the system handles initial user volume. | - Login API target is validated - Dropdown API performance is validated - Self-assessment load target is validated - Dashboard load target is validated - Excel import 500 rows target is validated | High | 5 | Demo 11 | SMP-US-080 | QA | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-094 | E16 - Testing, Quality and UAT | M19 | Prepare UAT scenarios and sign-off pack | Scrum Master / QA | As a Product Owner, I want UAT scenarios so that business users can validate the end-to-end workflow. | - UAT scenarios cover Admin, Lead Manager and Technician - ATLAS-deZentral pilot data is included - Expected results are documented - Defect tracking process is defined - Sign-off template is prepared | Highest | 5 | Demo 11 | SMP-US-091 | QA | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-095 | E17 - DevOps, Deployment and Production Readiness | M18 | Create CI/CD pipeline | DevOps Engineer | As a DevOps engineer, I want automated build and deployment so that releases are repeatable. | - Backend build runs mvn clean verify - Frontend build runs npm test and ng build - Docker image is built - Artifacts are versioned - Pipeline fails on test or quality gate failure | High | 8 | Demo 11 | SMP-US-089 | DevOps | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-096 | E17 - DevOps, Deployment and Production Readiness | M18 | Containerize backend and frontend | DevOps Engineer | As a DevOps engineer, I want Docker packaging so that the application can be deployed consistently. | - Backend Dockerfile is created - Frontend build artifact deployment approach is documented - Local docker-compose can run backend + database if required - Health checks are configured - No secrets are embedded in images | High | 5 | Demo 11 | SMP-US-005,SMP-US-006 | DevOps | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-097 | E17 - DevOps, Deployment and Production Readiness | M18 | Prepare QA environment deployment | DevOps Engineer | As a QA team, I want a stable QA environment so that SIT and UAT can be executed. | - QA backend is deployed - QA frontend is deployed - QA database migration is applied - Environment variables/secrets are configured - Smoke test passes | Highest | 8 | Demo 11 | SMP-US-095,SMP-US-096 | DevOps | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-098 | E17 - DevOps, Deployment and Production Readiness | M18 | Prepare production environment deployment | DevOps Engineer | As the project team, I want production infrastructure prepared so that go-live can happen safely. | - Production database is provisioned - Secrets are configured securely - Backend and frontend deployment runbook is ready - Rollback plan is documented - Smoke test checklist is ready | Highest | 8 | Demo 12 | SMP-US-097,SMP-US-094 | DevOps | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-099 | E17 - DevOps, Deployment and Production Readiness | M20 | Create user guides and support runbook | Scrum Master / Support Lead | As a support team, I want user guides and runbooks so that the application can be supported after go-live. | - Admin guide is prepared - Lead Manager guide is prepared - Technician guide is prepared - Production support runbook is prepared - Known issues and FAQ are documented | High | 5 | Demo 12 | SMP-US-094 | Documentation | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-100 | E17 - DevOps, Deployment and Production Readiness | M20 | Execute production go-live and handover | Project Team | As the business owner, I want a controlled go-live so that users can start using the platform with minimal risk. | - Production smoke test passes - Initial admin users are validated - Pilot application data is validated - Support contact and escalation path are published - Go-live sign-off is recorded | Highest | 8 | Demo 12 | SMP-US-098,SMP-US-099 | Release | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-101 | E18 - Future SSO Readiness | M17 | Document future SSO integration approach | Architect | As an Architect, I want future SSO readiness documented so that local login can later be replaced with company identity provider integration. | - Company User ID mapping to users.username is documented - SSO claim mapping for username/email/employee ID is documented - Local login fallback strategy is documented - No direct company DB password validation is proposed - Future user_external_identities migration is listed as optional | Medium | 3 | Post-Go-Live | SMP-US-018 | Architecture | skill-matrix,java21,springboot3,angular17,mysql8
Story | SMP-US-102 | E18 - Future SSO Readiness | M17 | Create SSO integration spike | Architect / Developer | As a project team, I want a technical spike for SSO so that effort and security approvals are understood after MVP launch. | - Identity provider option is identified - OAuth2/OIDC or SAML approach is compared - Required approvals and access are listed - Impact on existing users table is assessed - Implementation backlog is created | Medium | 5 | Post-Go-Live | SMP-US-101 | Architecture | skill-matrix,java21,springboot3,angular17,mysql8

## Demo Plan
Demo Milestone | Theme | Story Range | What to Demonstrate | Exit Criteria
Demo 0 | Backlog and Design Freeze | SMP-US-001 to SMP-US-004 | Show finalized scope, Jira structure, DoR/DoD, architecture/design baseline. No production code demo required. | Agreement to start development.
Demo 1 | Foundation and Database | SMP-US-005 to SMP-US-017 | Show backend startup, Angular shell, Flyway migration, seeded DB, Swagger, Actuator, verification queries. | Technical foundation accepted.
Demo 2 | Authentication and RBAC | SMP-US-018 to SMP-US-024 | Show login using Company User ID, first-login password change, role-based menus, 401/403 behavior. | Security/login flow accepted.
Demo 3 | Application Hierarchy | SMP-US-025 to SMP-US-031 | Show lookup management and WEB/HOST + B06/B12/B20 cascading dropdowns with active/deprecated application behavior. | Application context model accepted.
Demo 4 | Users and Technician Assignment | SMP-US-032 to SMP-US-040 | Show bulk user upload, user management, roles, teams, multi-application technician assignment and assignment import. | 140-technician onboarding approach accepted.
Demo 5 | Skill Master and Skill Imports | SMP-US-041 to SMP-US-047 | Show three skill categories, common technical skill import once, app-specific skill import for ATLAS/AVUS, rating scale. | Skill governance approach accepted.
Demo 6 | Requirement Version and Expected Ratings | SMP-US-048 to SMP-US-053 | Show ATLAS requirement version, expected ratings, publish/approve/reject flow, requirement mapping import. | Approved requirement baseline ready for assessment.
Demo 7 | Assessment Cycle and Technician Self Assessment | SMP-US-054 to SMP-US-062 | Show open cycle, technician sees assigned app only, expected level hidden, save draft, submit final. | Technician workflow accepted.
Demo 8 | Lead Review and Gap Calculation | SMP-US-063 to SMP-US-071 | Show pending review, manager ratings, row decisions, bulk actions, overall approval/return, gap snapshot generation. | Lead Manager workflow accepted.
Demo 9 | Training and Dashboard | SMP-US-072 to SMP-US-077 | Show training recommendations, priority/target dates, dashboard summary, readiness, heatmap and coverage risk. | Management visibility accepted.
Demo 10 | Reports, Exports, Audit and Notifications | SMP-US-078 to SMP-US-088 | Show report filters, Excel export, import history, audit log, notification drawer and event notifications. | Operational traceability accepted.
Demo 11 | QA, UAT and Deployment Readiness | SMP-US-089 to SMP-US-097 | Show test coverage, API tests, E2E tests, security/performance results and QA deployment. | Release candidate accepted for UAT.
Demo 12 | Production Go-Live and Handover | SMP-US-098 to SMP-US-100 | Show production smoke test, runbooks, user guides, support readiness and sign-off pack. | Go-live approved.
Post-Go-Live | Future SSO Readiness | SMP-US-101 to SMP-US-102 | Show SSO approach, company identity mapping, required approvals and future implementation backlog. | SSO roadmap accepted.

## Epic Summary
Epic | Story Count | Total Story Points | Main Demo Milestone
E01 - Project Readiness and Design Freeze | 4 | 10 | Demo 0
E02 - Project Foundation and Local Environment | 7 | 23 | Demo 1
E03 - Database, Flyway and Reference Data | 6 | 28 | Demo 1
E04 - Authentication, RBAC and First Login Security | 7 | 41 | Demo 2
E05 - Lookup and Application Hierarchy | 7 | 41 | Demo 3
E06 - User, Team and Technician Assignment | 9 | 63 | Demo 4
E07 - Skill Master and Rating Scale | 7 | 45 | Demo 5
E09 - Requirement Version and Expected Ratings | 6 | 45 | Demo 6
E10 - Assessment Cycle | 3 | 16 | Demo 7
E11 - Technician Self Assessment | 6 | 39 | Demo 7
E12 - Lead Manager Review and Approval | 7 | 44 | Demo 8
E13 - Gap Analysis and Training Recommendation | 5 | 34 | Demo 8, Demo 9
E14 - Dashboard and Reports | 7 | 44 | Demo 10, Demo 9
E08 - Excel Import and Export | 2 | 10 | Demo 10
E15 - Audit Log and Notifications | 5 | 31 | Demo 10
E16 - Testing, Quality and UAT | 6 | 36 | Demo 11
E17 - DevOps, Deployment and Production Readiness | 6 | 42 | Demo 11, Demo 12
E18 - Future SSO Readiness | 2 | 8 | Post-Go-Live

## README
Skill Matrix Platform - JIRA Backlog
Purpose | Use this workbook to create Epics and Stories in JIRA.
Recommended JIRA flow | Create Epics first, then import User Stories and map Epic field accordingly.
Story Points | Indicative only. Re-estimate during sprint planning.
Demo Milestone | Use this to decide which stories should be shown in each sprint/client demo.
Definition of Done | Code complete, tests pass, API/UI integrated where applicable, role access verified, demo-ready.